## Project Plan
Project Name : Koyl (AI Healthcare)
MODULE | Developer | Start date | End date | Status
Week 1 (5 working Days) |  | 2024-06-24 | 2024-06-28
Requirements Specifications | Jatinder
Architecture Setup (Backend , Frontend) | vipin/Dharmendra
Backend project Setup
Frontent Project Setup
POC with R&D items | Vipin/Dharmendra
POC with chatgpt implementation to get required data
Patients Singup
Singup with Api and Singin with goggle for paitent
Docter Login authentication with database and goggle,Logout functionality
UI/UX Figma Design | Hitanshi
paitent singup,Docter login Design
patients facing react js template
Week 2(5 Working days) |  | 2024-07-01 | 2024-07-05
Backend | Vipin
Chatgpt Api integration,Patients list Api,search api for find paitent
Frontend | Vipin/Dharmendra
Seach functionality for Symtoms and diseses
massage functionality using twillo
UI/UX Figma Design | Hitanshi
Docter Dashboard page ,Sindenav and header
save reccomondation page with static data,Recommdation page Design
Week 3 (5 working day) |  | 2024-07-08 | 2024-07-12
UI/UX Design | Hitanshi
Open share model and share button click
model for add new patient
Patients details page
Patients page remove account model | vipin/Manvendra
Frontend
Sort Paitent functionality,pagination functionality and goto page for patient
Bakend
Remove patient Account api | vipin/Dharmendra
save recommendation data api
api for patient details
Week 4 (5 working days) |  | 2024-07-15 | 2024-07-19
UI/UX Design | Hitanshi
Message recieve from docter for diet plan
my recommendation page with chatgpt data
Grosery checklist with chatgpt data
how did it go page
thanks for info page
special offer page with static data
Frontend | Vipin/Dharmendra
my recommendation page option 1 functionality
my recommendation page work option 2 functionality
Account deleted toster message,Account creation for docter functionality
Backend
My recommendation page option 2 provide link of other website to order food
Week 5(5 days working) |  | 2024-07-22 | 2024-07-26
frontend | Vipin/Manvendra
patients list check in log functionality
Back to home routing funtionality
Accordion sources functionality redirected to chatgpt page
Week 6 (5 days working) |  | 2024-07-29 | 2024-08-02
Frontend | Vipin/Manvendra
spacial offer page functionality navitage to different site to order Item
dietry progress functionality massage functionality using twillo
Code refectoring and code review
Week 7 (5 days working) |  | 2024-08-05 | 2024-08-09
hosting, /integration and unit teating